## Sheet1
CHANGE NO. | CHANGE TYPE | DESCRIPTION | DATE IDENTIFIED | STATUS | PRIORITY | ASSIGNED TO | RESOLUTION EXPECTED | ACTION | AREA OF IMPACT | ESCALATION REQUIRED | DATE RESOLVED
1 | Model Update | Switched from pre-trained CSRNet to training from scratch using JHU-CROWD++ dataset | 2025-01-30 | In Progress | Medium | Oudat Shabbir | Immediately | Implement and retrain CSRNet | Model Accuracy | NO | 1/30/25
2 | Model Update | Switched from pre-trained MCNN to training from strach using Shanghai-tech dataset | 2025-01-30 | In Progress | Medium | Uswat Yusuf | Immediately | Implement and retrain MCNN | Model Accuracy | No | 1/30/25
2 | Dataset Change | Added fine-tuning dataset from Giraffe and Graduation events | 11/16/20XX | OpenOpen | High | Oudat Shabbir | 1 Week | Preprocess and augment dataset | Data Processing | YES
3 | Code Optimization | Improved model inference speed in Google Colab Pro | 11/30/20XX | Approved | Medium | Oudat Shabbir | 2 Weeks | Optimize batch processing | Model Performance | NO
| Evaluation Metric Change | Switched from MAE to RMSE for better performance evaluation |  | In Progress | Low | Oudat Shabbir |  | Implement metric change in evaluation script | Model Evaluation
Rejected