## EXAMPLE - OKR Grading Scale
OKR GRADING SCALE SCORECARD TEMPLATE
| OVERALL SCORE | 0.65
ID | DESCRIPTION | OUTCOME | OKR SCORE | OWNERS | NOTES
OBJ-1 | Increase Sales | OBJECTIVE FINAL SCORE | 0.53333
KR-1 | Reach a 25% conversion rate on all leads | Reached 15% | 0.6
KR-2 | Reduce time spent in the sale cycle by 20% | Reduced by 8% | 0.3
KR-3 | Open 5 new stores | Opened 4 | 0.7
OBJ-2 | Bolster Network Security | OBJECTIVE FINAL SCORE | 0.76667
KR-1 | Implement new backup system by end of Q2 | Implemented and working | 1
KR-2 | Enable 2FA for employees and customers | 60% of users signed up for new approach | 0.6
KR-3 | Research and analyze 3 SIEM platforms | 2 out of 3 researched | 0.7
OBJ-3 | Objective 3 description | OBJECTIVE FINAL SCORE | –
KR-1 | Key Result 1 description |  | –
KR-2 | Key Result 2 description |  | –
KR-3 | Key Result 3 description |  | –
KR-4 | Key Result 4 description |  | –
OBJ-4 | Objective 4 description | OBJECTIVE FINAL SCORE | –
KR-1 | Key Result 1 description |  | –
KR-2 | Key Result 2 description |  | –
KR-3 | Key Result 3 description |  | –
KR-4 | Key Result 4 description |  | –
OBJ-5 | Objective 5 description | OBJECTIVE FINAL SCORE | –
KR-1 | Key Result 1 description |  | –
KR-2 | Key Result 2 description |  | –
KR-3 | Key Result 3 description |  | –
KR-4 | Key Result 4 description |  | –
CLICK HERE TO CREATE IN SMARTSHEET
OVERALL SCORE CALCULATION – do not delete –
[6 empty] | OBJ-1 | 0.53333
[6 empty] | OBJ-2 | 0.76667
[6 empty] | OBJ-3 | –
[6 empty] | OBJ-4 | –
[6 empty] | OBJ-5 | –

## OKR Grading Scale Scorecard
Overall Score calculates automatically; do not alter cell.
| OVERALL SCORE | 0.82
ID | DESCRIPTION | OUTCOME | OKR SCORE | OWNERS | NOTES
OBJ-1 | Research existing theoretical concepts, tools, and techniques for crowd engagement and analysis by conducting a systematic literature review | Done/ Success | 0.8
KR-1 | Complete a systematic literature review and summarize findings in a report by December 2024. | Team members did individual research on selected topics with a recommendation plan | 0.8
KR-2 | Identify and categorize at least 3 existing crowd engagement and analysis techniques and models by January 2025. | Three models Have been identified (MCNN, YOLO, CSRNet) | 0.6
KR-3 | Create a PowerPoint presentation of research findings for stakeholders. | Created a powerpoint presentation and uploaded to group blog | 1
OBJ-2 | Collect live event images from Bradford City of Culture 2025 events and graduations for model training. | Done/ Success | 0.75
KR-1 | Gather at least 2,000 high-quality crowd images from three different events ensuring diversity in crowd size, lighting conditions, and viewpoints by September 2025. | Images were obtained from the graduation event in December, and other events in city centre. | 0.8
KR-2 | Have images returned and saved to a folder. | Images were saved to a folder which is shared by team members. | 0.7
OBJ-3 | Create a labelled dataset through data annotation. | Done/ Success | 0.6
KR-1 | Manually annotate at least 50% of the collected dataset with bounding boxes or density maps by late March 2025. | Only 10% of images were annotated which were combined with public dataset | 0.4
KR-2 | Validate and refine at least 95% of labelled data through a quality assurance process by April 2025. | Done | 0.8
OBJ-4 | Design, develop and evaluate a custom deep learning model for crowd counting. | Done/ Success | 0.95
KR-1 | Develop the first functional prototype of the model.(Version 1) | Developed a CSRNet model for crowd density estimation and crowd counting, developed a YOLO model for crowd tracking using bounding boxes | 1
KR-2 | Evaluate the performance of models using performance metrics: MAE and MSE. | Initial model had a MAE of about 120. | 0.9
OBJ-5 | Optimize the developed models to improve performance | Done/ Success | 1
KR-1 | The performance of the model should be improved. | Improved/ tuned model had an MAE of 90. | 1
KR-2 | By March 2025, perform model comparison and select the best-performing model based on predefined evaluation criteria. | The VGG model and CSRNet model were compared after evaluation and testing and CSRNet model was chosen. | 1
OBJ-6 | Create design patterns, UML diagrams and pipelines for the project | Done/ Success | 0.8
KR-1 | Develop machine learning pipeline to guide the creation process by February 2025 | A machine learning pipeline was developed showing a high level view of the development process. | 0.8
KR-2 | Design pattern and UML diagrams should be developed by February 2025 | All design patterns and UML diagrams have been created and just need to be reviewed and improved on | 0.8
KR-3 | Ensure all design patterns are reviewed and updated by late March 2025, incorporating feedback from the team. | Class diagram was edited to match the final code, machine learning pipeline and workflow pipeline to display the change from MCNN model to VGG architecture. | 1
OBJ-7 | Implement agile project management and agile quality techniques | Done/ Success | – |  |  | OVERALL SCORE CALCULATION – do not delete –
KR-1 | Delegate tasks for each sprint, ensuring at least 80% task completion rate per sprint. | All tasks were delegated among team memebers. Most tasks were done together to ensure every individual is gaining knowledge and also because there's less people in the team | 1 |  |  | OBJ-1 | 0.8
KR-2 | Conduct retrospectives at the end of each sprint with a focus on identifying at least 2 process improvements. | All retrospectives have added to the sprint review table highlighting both good and bad experiences and how they could be improved. | 1 |  |  | OBJ-2 | 0.75
OBJ-8 | Create a github repository for file management and code maintainability | Done/ Success | – |  |  | OBJ-3 | 0.6
KR-1 | Add a README file to give a high level overview of the project, its development process and how it could be implemented and improved. | Done | 0.9 |  |  | OBJ-4 | 0.95
KR-2 | Upload all files including: Project Initiation Documents (PID), code files and presentation. | Done | 1 |  |  | OBJ-5 | 1
OBJ-9 | Test and validate the effectiveness of the developed models and the system as a whole |  | –
KR-1 | Develop test plans for each stage of the system’s development. | Test plans, unit and integration tests have been done | 0.8
KR-2 | Perform model validation using existing datasets and metrics | Model was tested on selected images from UCF_QNRH | 0.8
OBJ-10 | Develop an external framework (website or chatbot) for user interaction and engagement with crowd analysis insights. |  | –
KR-1 | Ensure the website is user-friendly and capable of providing real-time crowd analysis insights within 5 seconds. | The website works well but the time to load the model is a bit long and also the inference time differs based on the size of the image (which is to be fixed) | 0.7
KR-2 | The website ahould have features including image upload, submit button, generated density map download functionality, functionality to handle large files. | It has all functionalities except the one to handle large files currently. | 0.7

## Scale - Do Not Delete
OKR REVIEW SCALE | [10 empty] | OKR REVIEW SCALE KEY
0 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9 | 1 | 0
0.1
0.2
0.3
0.4
0.5
0.6
0.7
0.8
0.9
1
–

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.